## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 3 | Iyas K | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 3 | Muhammed Sinan | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Norah Elizabeth Biju | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Bhogyam venkata sai Likhitha | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Ogeti Aravind | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Mahesh D | DevOps Engineer | Week 1 | No

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
1 | Deploying a monolithic application | 2026-02-23 | 2026-02-26 | Deploying an app in EC2 instance where web app, backend, and database are deployed in public, private, and RDS respectively
2 | Deploying a microservices architecture application | 2026-02-25 | 2026-02-26 | Change the app into a microservice architecture and deploy it using EC2 and RDS
3 | Creating our own Docker images using docker build | 2026-02-26 | 2026-02-28 | Creating our own Docker image
4 | Implemented multi-tier applications across different containers using host gateway | 2026-03-02 | 2026-03-03 | Working with multi-tier app using host gateway
5 | Implemented multi-tier applications across different containers using custom network and stored backups using volumes | 2026-03-03 | 2026-03-04 | Working with multi-tier app using networks and volumes

## Task_Tracking(23-02)
Sprint | Team | Task ID | Description | Assigned To | Story Point | Status | Reviewer
1 | Team 3 | T2-001 | Web app deployed properly configuring backend deployment | Iyas K | 3 | Done
1 | Team 3 | T2-002 | Web app deployed properly configuring backend deployment | Muhammed Sinan | 3 | Done
1 | Team 3 | T2-003 | Web app deployed properly configuring backend deployment | Norah Elizabeth Biju | 3 | Done
1 | Team 3 | T2-004 | Web app deployed properly configuring backend deployment | Bhogyam Venkata Sai Likhitha | 3 | Done
1 | Team 3 | T2-005 | Web app deployed properly configuring backend deployment | Ogeti Aravind | 3 | Done
1 | Team 3 | T2-006 | Configuring microservices architecture | Mahesh D | 3 | Done
2 | Team 3 | T2-007 | Configuring and deploying microservices in EC2 instances and connecting RDS | Iyas K | 4 | Done
2 | Team 3 | T2-008 | Configuring and deploying microservices in EC2 instances and connecting RDS | Muhammed Sinan | 4 | Done
2 | Team 3 | T2-009 | Configuring and deploying microservices in EC2 instances and connecting RDS | Norah Elizabeth Biju | 4 | Done
2 | Team 3 | T2-010 | Configuring and deploying microservices in EC2 instances and connecting RDS | Bhogyam Venkata Sai Likhitha | 4 | Done
2 | Team 3 | T2-011 | Configuring and deploying microservices in EC2 instances and connecting RDS | Ogeti Aravind | 4 | Done
2 | Team 3 | T2-012 | Configuring and deploying microservices in EC2 instances and connecting RDS | Mahesh D | 4 | Done
3 | Team 3 | T2-013 | Creating our own Docker images using docker build | Iyas K | 3 | Done
3 | Team 3 | T2-014 | Creating our own Docker images using docker build | Muhammed Sinan | 3 | Done
3 | Team 3 | T2-015 | Creating our own Docker images using docker build | Norah Elizabeth Biju | 3 | Done
3 | Team 3 | T2-016 | Creating our own Docker images using docker build | Bhogyam Venkata Sai Likhitha | 3 | Done
3 | Team 3 | T2-017 | Creating our own Docker images using docker build | Ogeti Aravind | 3 | Done
3 | Team 3 | T2-018 | Creating our own Docker images using docker build | Mahesh D | 3 | Done
3 | Team 3 | T2-019 | Implemented multi tier applications across different containers using host gateway | Iyas K | 4 | Done
3 | Team 3 | T2-020 | Implemented multi tier applications across different containers using host gateway | Muhammed Sinan | 4 | Done
3 | Team 3 | T2-021 | Implemented multi tier applications across different containers using host gateway | Norah Elizabeth Biju | 4 | Done
3 | Team 3 | T2-022 | Implemented multi tier applications across different containers using host gateway | Bhogyam Venkata Sai Likhitha | 4 | Done
3 | Team 3 | T2-023 | Implemented multi tier applications across different containers using host gateway | Ogeti Aravind | 4 | Done
3 | Team 3 | T2-024 | Implemented multi tier applications across different containers using host gateway | Mahesh D | 4 | Done
3 | Team 3 | T2-025 | Implemented multi tier applications across different containers using custom network and stored backups using volumes | Iyas K | 4 | Done
3 | Team 3 | T2-026 | Implemented multi tier applications across different containers using custom network and stored backups using volumes | Muhammed Sinan | 4 | Done
3 | Team 3 | T2-027 | Implemented multi tier applications across different containers using custom network and stored backups using volumes | Norah Elizabeth Biju | 4 | Done
3 | Team 3 | T2-028 | Implemented multi tier applications across different containers using custom network and stored backups using volumes | Bhogyam Venkata Sai Likhitha | 4 | Done
3 | Team 3 | T2-029 | Implemented multi tier applications across different containers using custom network and stored backups using volumes | Ogeti Aravind | 4 | Done
3 | Team 3 | T2-030 | Implemented multi tier applications across different containers using custom network and stored backups using volumes | Mahesh D | 4 | Done

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | CI/CD Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -