## Team_Mapping
Batch | Team | Member Name | Role | Week | Scrum Master?
Batch 1 | Team 3 | Iyas K | DevOps Engineer | Week 1 | Yes
Batch 1 | Team 3 | Muhammed Sinan | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Norah Elizabeth Biju | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Bhogyam venkata sai Likhitha | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Ogeti Aravind | DevOps Engineer | Week 1 | No
Batch 1 | Team 3 | Mahesh D | DevOps Engineer | Week 2 | Yes

## Sprint-Overview
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | Linux & AWS Overview | 2026-02-17 | 2026-02-18 | Understanding Linux commands and AWS Services
Sprint 2 | EC2 Instances & VPC | 2026-02-19 | 2026-02-20 | Hands‑on with EC2 and VPC
Sprint 3 | Load Balancers,Subnets, Internet Gateways & NAT Gateways | 2026-02-21 | 2026-02-23 | Setting Up Load Balancers,Public/Private Subnets with IGW & NAT Gateways
Sprint 4 | RDS & 3-Tier Devops Architecture | 2026-02-24 | 2026-02-25 | Fullstack Monolithic App with Frontend, Backend & RDS in 3-Tier Devops Architecture
Sprint 5 | DevOps Worflow, Hardware Level Virtualization and Containerization | 2026-02-26 | 2026-03-02 | Understanding Devops Worflow, hardware virtualization concepts, disadvantages of VMs and Docker Containerization
Sprint 6 | Docker Networking and Compose | 2026-03-03 | 2026-03-04 | Creating containers and images, custom network
|  | 2026-03-05 | 2026-03-05 | Module 1 evaluation presentation
Sprint 7 | Docker disadvantages and docker swarm | 2026-03-06 | 2026-03-07 | Understanding the disadvantages of Docker containers, and the limitations in Docker Swarm
Sprint 8 | Kubernetes Components and Introduction | 2026-03-09 | 2026-03-11 | Understanding the Kubernetes components, its architecture, how components communicate, api server, setting up our own clusters, deep diving into the workflow behind each command of creating control plane, pods and its life cycle.
Sprint 9 | Implementation of Replicaset, Deployment ans services | 2026-03-12 | 2026-03-14 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart
Sprint 10 | Explore configmap, secrets and Metrics server, expose application | 2026-03-16 | 2026-03-18 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB
Sprint 11 | Explore API Gateway, Gateway API and K-Gateway | 2026-03-19 | 2026-03-19 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute.
Sprint12 | Explore GatewayAPI Advanced Topics | 2026-03-23 | 2026-03-23 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services.
Sprint13 | Kubernetes Volumes | 2026-03-24 | 2026-03-25 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting.
Sprint 14 | Explored about the kubernetes components | 2026-03-26 | 2026-03-26 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints.
Sprint 15 | Implemented dynamic provisioning using NFS in Kubernetes | 2026-03-27 | 2026-03-27 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB.
Sprint 16 | Implemented Kubernetes StatefulSet Communication & Headless Services | 2026-03-28 | 2026-03-28 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring.
Sprint 17 | Helm Chart Development and Deployment Automation | 2026-03-30 | 2026-03-30 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction.
Sprint 18 | Worked on our own microservices | 2026-03-31 | 2026-04-01 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details.
Sprint 19 | Kubernetes Authentication & RBAC Foundations | 2026-04-02 | 2026-04-02 | Explored certificates, keys, kubeconfig contexts, and OIDC,set up Keycloak for identity management. Generated key, CSR, and certificates, and implemented RBAC using Roles and Bindings.
Sprint 20 | Service Account Implementation | 2026-04-03 | 2026-04-03 | Learned how Kubernetes Service Accounts provide identity to pods. Implemented secure communication between workloads and the API server using service accounts.
Sprint 21 | Advanced Scheduling with Affinity Rules | 2026-04-04 | 2026-04-04 | Implemented node affinity, pod affinity, and pod anti-affinity for intelligent scheduling. Controlled pod placement based on node characteristics and inter-pod relationships.
Sprint 22 | Cluster Control & Policy Enforcement | 2026-04-06 | 2026-04-06 | Worked with taints and tolerations to restrict pod scheduling on nodes. Explored admission controllers and policy enforcement using OPA and Kyverno.
Sprint 23 | Dashboard & CI/CD Workflow Setup | 2026-04-07 | 2026-04-07 | Deployed Kubernetes Dashboard for cluster monitoring and management. Learned Git, GitHub Actions, branch protection rules, and built CI/CD workflow syntax.
Sprint 24 | SonarQube Cloud Setup & SAST Scanning | 2026-04-09 | 2026-04-09 | Configured SonarQube Cloud and performed SAST scanning with quality gate checks.
Sprint 25 | Snyk Dependency Scanning | 2026-04-10 | 2026-04-10 | Used Snyk to scan and identify vulnerabilities in project dependencies.
Sprint 26 | SonarQube Server Setup,Snyk Setup & CI Integration | 2026-04-11 | 2026-04-11 | Set up SonarQube server and integrated it into CI pipeline for automated code analysis,snyk Integrated with the CI Pipeline
Sprint 27 | CI Pipeline for Docker Build, Trivy Scan & Push | 2026-04-13 | 2026-04-14 | Implemented CI pipeline to build Docker images, perform Trivy image scanning, and push to DockerHub.

## Task_Tracking(23-02)
Sprint | Team | TaskID | Description | AssignedTo | StoryPoint | Status | Reviewer
Sprint 1 | Team 3 | T1-001 | Understand Linux commands and AWS Services | Iyas K | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-002 | Understand Linux commands and AWS Services | Muhammed Sinan | 2 | Done | Norah Elizabeth Biju
Sprint 1 | Team 3 | T1-003 | Understand Linux commands and AWS Services | Norah Elizabeth Biju | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-004 | Understand Linux commands and AWS Services | Bhogyam venkata sai Likhitha | 2 | Done | Mahesh D
Sprint 1 | Team 3 | T1-005 | Understand Linux commands and AWS Services | Ogeti Aravind | 2 | Done | Trainer
Sprint 1 | Team 3 | T1-006 | Understand Linux commands and AWS Services | Mahesh D | 2 | Done | Iyas K
Sprint 2 | Team 3 | T2-001 | Set up EC2 Instances , Configure VPC & Security groups | Iyas K | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-002 | Set up EC2 Instances , Configure VPC & Security groups | Muhammed Sinan | 3 | Done | Ogeti Aravind
Sprint 2 | Team 3 | T2-003 | Set up EC2 Instances , Configure VPC & Security groups | Norah Elizabeth Biju | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-004 | Set up EC2 Instances , Configure VPC & Security groups | Bhogyam venkata sai Likhitha | 3 | Done | Muhammed Sinan
Sprint 2 | Team 3 | T2-005 | Set up EC2 Instances , Configure VPC & Security groups | Ogeti Aravind | 3 | Done | Trainer
Sprint 2 | Team 3 | T2-006 | Set up EC2 Instances , Configure VPC & Security groups | Mahesh D | 3 | Done | Norah Elizabeth Biju
Sprint 3 | Team 3 | T3-001 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Iyas K | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-002 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Muhammed Sinan | 4 | Done | Mahesh D
Sprint 3 | Team 3 | T3-003 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Norah Elizabeth Biju | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-004 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Bhogyam venkata sai Likhitha | 4 | Done | Iyas K
Sprint 3 | Team 3 | T3-005 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Ogeti Aravind | 4 | Done | Trainer
Sprint 3 | Team 3 | T3-006 | Set Up Load Balancers,Configure Public/Private Subnets with IGW & NAT Gateways | Mahesh D | 4 | Done | Bhogyam venkata sai Likhitha
Sprint 4 | Team 3 | T4-001 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Iyas K | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-002 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Muhammed Sinan | 6 | Done | Norah Elizabeth Biju
Sprint 4 | Team 3 | T4-003 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-004 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Bhogyam venkata sai Likhitha | 6 | Done | Mahesh D
Sprint 4 | Team 3 | T4-005 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Ogeti Aravind | 6 | Done | Trainer
Sprint 4 | Team 3 | T4-006 | Setup RDS & Deploy a 3-Tier Monolithic architecture | Mahesh D | 6 | Done | Iyas K
Sprint 5 | Team 3 | T5-001 | Create Container and deployed image for monolithic application | Iyas K | 4 | Done | Iyas K
Sprint 5 | Team 3 | T5-002 | Create Container and deployed image for monolithic application | Muhammed Sinan | 4 | Done | Trainer
Sprint 5 | Team 3 | T5-003 | Create Container and deployed image for monolithic application | Norah Elizabeth Biju | 4 | Done | Norah Elizabeth Biju
Sprint 5 | Team 3 | T5-004 | Create Container and deployed image for monolithic application | Bhogyam venkata sai Likhitha | 4 | Done | Trainer
Sprint 5 | Team 3 | T5-005 | Create Container and deployed image for monolithic application | Ogeti Aravind | 4 | Done | Mahesh D
Sprint 5 | Team 3 | T5-006 | Create Container and deployed image for monolithic application | Mahesh D | 4 | Done | Trainer
Sprint 6 | Team 3 | T6-001 | Created custom network and deplyed microservices in multiple containers | Iyas K | 5 | Done | Mahesh D
Sprint 6 | Team 3 | T6-002 | Created custom network and deplyed microservices in multiple containers | Muhammed Sinan | 5 | Done | Trainer
Sprint 6 | Team 3 | T6-003 | Created custom network and deplyed microservices in multiple containers | Norah Elizabeth Biju | 5 | Done | Ogeti Aravind
Sprint 6 | Team 3 | T6-004 | Created custom network and deplyed microservices in multiple containers | Bhogyam venkata sai Likhitha | 5 | Done | Trainer
Sprint 6 | Team 3 | T6-005 | Created custom network and deplyed microservices in multiple containers | Ogeti Aravind | 5 | Done | Muhammed Sinan
Sprint 6 | Team 3 | T6-006 | Created custom network and deplyed microservices in multiple containers | Mahesh D | 5 | Done | e
Sprint 7 | Team 3 | T7-001 | Containerized microservice application with services in two different network and initialized a gateway for communication | Iyas K | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-002 | Containerized microservice application with services in two different network and initialized a gateway for communication | Muhammed Sinan | 5 | Done | Mahesh D
Sprint 7 | Team 3 | T7-003 | Containerized microservice application with services in two different network and initialized a gateway for communication | Norah Elizabeth Biju | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-004 | Containerized microservice application with services in two different network and initialized a gateway for communication | Bhogyam venkata sai Likhitha | 5 | Done | Iyas K
Sprint 7 | Team 3 | T7-005 | Containerized microservice application with services in two different network and initialized a gateway for communication | Ogeti Aravind | 5 | Done | Trainer
Sprint 7 | Team 3 | T7-006 | Containerized microservice application with services in two different network and initialized a gateway for communication | Mahesh D | 5 | Done | Bhogyam venkata sai Likhitha
Sprint 8 | Team 3 | T8-001 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Iyas K | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-002 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Muhammed Sinan | 6 | Done | Norah Elizabeth Biju
Sprint 8 | Team 3 | T8-003 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-004 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Bhogyam venkata sai Likhitha | 6 | Done | Mahesh D
Sprint 8 | Team 3 | T8-005 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Ogeti Aravind | 6 | Done | Trainer
Sprint 8 | Team 3 | T8-006 | Set up our own cluster with worker and master nodes and created a pod with all possiblity of ststus such as success,pending,failed,running etc. | Mahesh D | 6 | Done | Iyas K
Sprint 9 | Team 3 | T9-001 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Iyas K | 7 | Done | Mahesh D
Sprint 9 | Team 3 | T9-002 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Muhammed Sinan | 7 | Done | Trainer
Sprint 9 | Team 3 | T9-003 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Norah Elizabeth Biju | 7 | Done | Ogeti Aravind
Sprint 9 | Team 3 | T9-004 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Bhogyam venkata sai Likhitha | 7 | Done | Trainer
Sprint 9 | Team 3 | T9-005 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Ogeti Aravind | 7 | Done | Muhammed Sinan
Sprint 9 | Team 3 | T9-006 | Implemented pods inside replicaset, deployment and created service, performed rollout, rollback maxUnavailable and maxUrge, pause, resume and restart | Mahesh D | 7 | Done | Norah Elizabeth Biju
Sprint 10 | Team 3 | T10-001 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Iyas K | 8 | Done | Mahesh D
Sprint 10 | Team 3 | T10-002 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Muhammed Sinan | 8 | Done | Trainer
Sprint 10 | Team 3 | T10-003 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Norah Elizabeth Biju | 8 | Done | Ogeti Aravind
Sprint 10 | Team 3 | T10-004 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Bhogyam venkata sai Likhitha | 8 | Done | Trainer
Sprint 10 | Team 3 | T10-005 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Ogeti Aravind | 8 | Done | Muhammed Sinan
Sprint 10 | Team 3 | T10-006 | implemented configmap, secrets and metrics server with request and limit, exposed application with Haproxy and implemented MetalLB | Mahesh D | 8 | Done | Norah Elizabeth Biju
Sprint 11 | Team 3 | T11-001 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Iyas K | 8 | Done | Trainer
Sprint 11 | Team 3 | T11-002 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Muhammed Sinan | 8 | Done | Norah Elizabeth Biju
Sprint 11 | Team 3 | T11-003 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 11 | Team 3 | T11-004 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Bhogyam venkata sai Likhitha | 8 | Done | Mahesh D
Sprint 11 | Team 3 | T11-005 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Ogeti Aravind | 8 | Done | Trainer
Sprint 11 | Team 3 | T11-006 | Studied API Gateway, Gateway API, KGateway, Ingress. Due to the limitations of Ingress, moved towards Gateway API for better flexibility and control. Installed KGateway and implemented it by exposing the web application using Gateway and HTTPRoute. | Mahesh D | 8 | Done | Bhogyam venkata sai Likhitha
Sprint 12 | Team 3 | T12-001 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Iyas K | 6 | Done | Trainer
Sprint 12 | Team 3 | T12-002 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Muhammed Sinan | 6 | Done | Ogeti Aravind
Sprint 12 | Team 3 | T12-003 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Norah Elizabeth Biju | 6 | Done | Trainer
Sprint 12 | Team 3 | T12-004 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Bhogyam venkata sai Likhitha | 6 | Done | Muhammed Sinan
Sprint 12 | Team 3 | T12-005 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Ogeti Aravind | 6 | Done | Trainer
Sprint 12 | Team 3 | T12-006 | Learned advanced concepts of Gateway API including GatewayClass, Gateway, HTTPRoute, and Controller. Implemented multiple HTTPRoute configurations and exposed the application by routing traffic between frontend and backend services. | Mahesh D | 6 | Done | Norah Elizabeth Biju
Sprint 13 | Team 3 | T13-001 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Iyas K | 7 | Done | Trainer
Sprint 13 | Team 3 | T13-002 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Muhammed Sinan | 7 | Done | Mahesh D
Sprint 13 | Team 3 | T13-003 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Norah Elizabeth Biju | 7 | Done | Trainer
Sprint 13 | Team 3 | T13-004 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Bhogyam venkata sai Likhitha | 7 | Done | Iyas K
Sprint 13 | Team 3 | T13-005 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Ogeti Aravind | 7 | Done | Trainer
Sprint 13 | Team 3 | T13-006 | Studied Kubernetes volumes including EmptyDir and HostPath. Learned about static and dynamic provisioning using PV, PVC, and StorageClasses. Implemented storage for MongoDB application and explored NFS for shared storage. Also analyzed OOM errors using shell scripting. | Mahesh D | 7 | Done | Bhogyam venkata sai Likhitha
Sprint 14 | Team 3 | T14-001 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Iyas K | 8 | Done | Trainer
Sprint 14 | Team 3 | T14-002 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Muhammed Sinan | 8 | Done | Mahesh D
Sprint 14 | Team 3 | T14-003 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 14 | Team 3 | T14-004 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Bhogyam venkata sai Likhitha | 8 | Done | Iyas K
Sprint 14 | Team 3 | T14-005 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Ogeti Aravind | 8 | Done | Trainer
Sprint 14 | Team 3 | T14-006 | Understanding container fundamentals, Docker image optimization, and Kubernetes networking including pod communication, DNS, and service-to-pod routing using endpoints. | Mahesh D | 8 | Done | Bhogyam venkata sai Likhitha
Sprint 15 | Team 3 | T15-001 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Iyas K | 8 | Done | Trainer
Sprint 15 | Team 3 | T15-002 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Muhammed Sinan | 8 | Done | Ogeti Aravind
Sprint 15 | Team 3 | T15-003 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 15 | Team 3 | T15-004 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Bhogyam venkata sai Likhitha | 8 | Done | Muhammed Sinan
Sprint 15 | Team 3 | T15-005 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Ogeti Aravind | 8 | Done | Trainer
Sprint 15 | Team 3 | T15-006 | Worked on NFS dynamic provisioning. Implemented dynamic storage provisioning using NFS CSI driver and validated persistence with MongoDB. | Mahesh D | 8 | Done | Norah Elizabeth Biju
Sprint 16 | Team 3 | T16-001 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Iyas K | 8 | Done | Trainer
Sprint 16 | Team 3 | T16-002 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Muhammed Sinan | 8 | Done | Norah Elizabeth Biju
Sprint 16 | Team 3 | T16-003 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 16 | Team 3 | T16-004 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Bhogyam venkata sai Likhitha | 8 | Done | Mahesh D
Sprint 16 | Team 3 | T16-005 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Ogeti Aravind | 8 | Done | Trainer
Sprint 16 | Team 3 | T16-006 | Learned StatefulSets, headless services, and implemented liveness/readiness probes for application health monitoring. | Mahesh D | 8 | Done | Bhogyam venkata sai Likhitha
Sprint 17 | Team 3 | T17-001 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Iyas K | 8 | Done | Trainer
Sprint 17 | Team 3 | T17-002 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Muhammed Sinan | 8 | Done | Mahesh D
Sprint 17 | Team 3 | T17-003 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 17 | Team 3 | T17-004 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Bhogyam venkata sai Likhitha | 8 | Done | Iyas K
Sprint 17 | Team 3 | T17-005 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Ogeti Aravind | 8 | Done | Trainer
Sprint 17 | Team 3 | T17-006 | Studied Helm charts structure including charts, values.yaml, conditional statements and loops for dynamic configuration, validated YAML file existence before loading, and understood Helm install execution flow including template rendering and Kubernetes API interaction. | Mahesh D | 8 | Done | Bhogyam venkata sai Likhitha
Sprint 18 | Team 3 | T18-001 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Iyas K | 8 | Done | Iyas K
Sprint 18 | Team 3 | T18-002 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Muhammed Sinan | 8 | Done | Trainer
Sprint 18 | Team 3 | T18-003 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Norah Elizabeth Biju | 8 | Done | Norah Elizabeth Biju
Sprint 18 | Team 3 | T18-004 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Bhogyam venkata sai Likhitha | 8 | Done | Trainer
Sprint 18 | Team 3 | T18-005 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Ogeti Aravind | 8 | Done | Mahesh D
Sprint 18 | Team 3 | T18-006 | Implemented and presented our microservices project implemented using Kubernetes concepts including deployments, services, gateway, configuration management, and scaling, explaining architecture, communication flow, and real-time implementation details. | Mahesh D | 8 | Done | Trainer
Sprint 19 | Team 3 | T19-001 | Explored certificates, keys, kubeconfig contexts, and OIDC,set up Keycloak for identity management. Generated key, CSR, and certificates, and implemented RBAC using Roles and Bindings. | Iyas K | 8 | Done | Trainer
Sprint 19 | Team 3 | T19-002 | Explored certificates, keys, kubeconfig contexts, and OIDC,set up Keycloak for identity management. Generated key, CSR, and certificates, and implemented RBAC using Roles and Bindings. | Muhammed Sinan | 8 | Done | Ogeti Aravind
Sprint 19 | Team 3 | T19-003 | Explored certificates, keys, kubeconfig contexts, and OIDC,set up Keycloak for identity management. Generated key, CSR, and certificates, and implemented RBAC using Roles and Bindings. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 19 | Team 3 | T19-004 | Explored certificates, keys, kubeconfig contexts, and OIDC,set up Keycloak for identity management. Generated key, CSR, and certificates, and implemented RBAC using Roles and Bindings. | Bhogyam venkata sai Likhitha | 8 | Done | Muhammed Sinan
Sprint 19 | Team 3 | T19-005 | Explored certificates, keys, kubeconfig contexts, and OIDC,set up Keycloak for identity management. Generated key, CSR, and certificates, and implemented RBAC using Roles and Bindings. | Ogeti Aravind | 8 | Done | Trainer
Sprint 19 | Team 3 | T19-006 | Explored certificates, keys, kubeconfig contexts, and OIDC,set up Keycloak for identity management. Generated key, CSR, and certificates, and implemented RBAC using Roles and Bindings. | Mahesh D | 8 | Done | Norah Elizabeth Biju
Sprint 20 | Team 3 | T20-001 | Learned how Kubernetes Service Accounts provide identity to pods. Implemented secure communication between workloads and the API server using service accounts. | Iyas K | 8 | Done | Trainer
Sprint 20 | Team 3 | T20-002 | Learned how Kubernetes Service Accounts provide identity to pods. Implemented secure communication between workloads and the API server using service accounts. | Muhammed Sinan | 8 | Done | Mahesh D
Sprint 20 | Team 3 | T20-003 | Learned how Kubernetes Service Accounts provide identity to pods. Implemented secure communication between workloads and the API server using service accounts. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 20 | Team 3 | T20-004 | Learned how Kubernetes Service Accounts provide identity to pods. Implemented secure communication between workloads and the API server using service accounts. | Bhogyam venkata sai Likhitha | 8 | Done | Iyas K
Sprint 20 | Team 3 | T20-005 | Learned how Kubernetes Service Accounts provide identity to pods. Implemented secure communication between workloads and the API server using service accounts. | Ogeti Aravind | 8 | Done | Trainer
Sprint 20 | Team 3 | T20-006 | Learned how Kubernetes Service Accounts provide identity to pods. Implemented secure communication between workloads and the API server using service accounts. | Mahesh D | 8 | Done | Bhogyam venkata sai Likhitha
Sprint 21 | Team3 | T21-001 | Implemented node affinity, pod affinity, and pod anti-affinity for intelligent scheduling. Controlled pod placement based on node characteristics and inter-pod relationships. | Iyas K | 8 | Done | Mahesh D
Sprint 21 | Team3 | T21-002 | Implemented node affinity, pod affinity, and pod anti-affinity for intelligent scheduling. Controlled pod placement based on node characteristics and inter-pod relationships. | Muhammed Sinan | 8 | Done | Trainer
Sprint 21 | Team3 | T21-003 | Implemented node affinity, pod affinity, and pod anti-affinity for intelligent scheduling. Controlled pod placement based on node characteristics and inter-pod relationships. | Norah Elizabeth Biju | 8 | Done | Ogeti Aravind
Sprint 21 | Team3 | T21-004 | Implemented node affinity, pod affinity, and pod anti-affinity for intelligent scheduling. Controlled pod placement based on node characteristics and inter-pod relationships. | Bhogyam venkata sai Likhitha | 8 | Done | Trainer
Sprint 21 | Team3 | T21-005 | Implemented node affinity, pod affinity, and pod anti-affinity for intelligent scheduling. Controlled pod placement based on node characteristics and inter-pod relationships. | Ogeti Aravind | 8 | Done | Muhammed Sinan
Sprint 21 | Team3 | T21-006 | Implemented node affinity, pod affinity, and pod anti-affinity for intelligent scheduling. Controlled pod placement based on node characteristics and inter-pod relationships. | Mahesh D | 8 | Done | Norah Elizabeth Biju
Sprint 22 | Team3 | T22-001 | Worked with taints and tolerations to restrict pod scheduling on nodes. Explored admission controllers and policy enforcement using OPA and Kyverno. | Iyas K | 8 | Done | Trainer
Sprint 22 | Team3 | T22-002 | Worked with taints and tolerations to restrict pod scheduling on nodes. Explored admission controllers and policy enforcement using OPA and Kyverno. | Muhammed Sinan | 8 | Done | Ogeti Aravind
Sprint 22 | Team3 | T22-003 | Worked with taints and tolerations to restrict pod scheduling on nodes. Explored admission controllers and policy enforcement using OPA and Kyverno. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 22 | Team3 | T22-004 | Worked with taints and tolerations to restrict pod scheduling on nodes. Explored admission controllers and policy enforcement using OPA and Kyverno. | Bhogyam venkata sai Likhitha | 8 | Done | Muhammed Sinan
Sprint 22 | Team3 | T22-005 | Worked with taints and tolerations to restrict pod scheduling on nodes. Explored admission controllers and policy enforcement using OPA and Kyverno. | Ogeti Aravind | 8 | Done | Trainer
Sprint 22 | Team3 | T22-006 | Worked with taints and tolerations to restrict pod scheduling on nodes. Explored admission controllers and policy enforcement using OPA and Kyverno. | Mahesh D | 8 | Done | Norah Elizabeth Biju
Sprint 23 | Team3 | T23-001 | Deployed Kubernetes Dashboard for cluster monitoring and management. Learned Git, GitHub Actions, branch protection rules, and built CI/CD workflow syntax. | Iyas K | 8 | Done | Mahesh D
Sprint 23 | Team3 | T23-002 | Deployed Kubernetes Dashboard for cluster monitoring and management. Learned Git, GitHub Actions, branch protection rules, and built CI/CD workflow syntax. | Muhammed Sinan | 8 | Done | Trainer
Sprint 23 | Team3 | T23-003 | Deployed Kubernetes Dashboard for cluster monitoring and management. Learned Git, GitHub Actions, branch protection rules, and built CI/CD workflow syntax. | Norah Elizabeth Biju | 8 | Done | Ogeti Aravind
Sprint 23 | Team3 | T23-004 | Deployed Kubernetes Dashboard for cluster monitoring and management. Learned Git, GitHub Actions, branch protection rules, and built CI/CD workflow syntax. | Bhogyam venkata sai Likhitha | 8 | Done | Trainer
Sprint 23 | Team3 | T23-005 | Deployed Kubernetes Dashboard for cluster monitoring and management. Learned Git, GitHub Actions, branch protection rules, and built CI/CD workflow syntax. | Ogeti Aravind | 8 | Done | Muhammed Sinan
Sprint 23 | Team3 | T23-006 | Deployed Kubernetes Dashboard for cluster monitoring and management. Learned Git, GitHub Actions, branch protection rules, and built CI/CD workflow syntax. | Mahesh D | 8 | Done | Iyas k
Sprint 24 | Team3 | T24-001 | Configured SonarQube Cloud and performed SAST scanning with quality gate checks. | Iyas K | 3 | Done | Trainer
Sprint 24 | Team3 | T24-002 | Configured SonarQube Cloud and performed SAST scanning with quality gate checks. | Muhammed Sinan | 3 | Done | Norah Elizabeth Biju
Sprint 24 | Team3 | T24-003 | Configured SonarQube Cloud and performed SAST scanning with quality gate checks. | Norah Elizabeth Biju | 3 | Done | Trainer
Sprint 24 | Team3 | T24-004 | Configured SonarQube Cloud and performed SAST scanning with quality gate checks. | Bhogyam venkata sai Likhitha | 3 | Done | Mahesh D
Sprint 24 | Team3 | T24-005 | Configured SonarQube Cloud and performed SAST scanning with quality gate checks. | Ogeti Aravind | 3 | Done | Trainer
Sprint 24 | Team3 | T24-006 | Configured SonarQube Cloud and performed SAST scanning with quality gate checks. | Mahesh D | 3 | Done | Iyas K
Sprint 25 | Team3 | T25-001 | Used Snyk to scan and identify vulnerabilities in project dependencies. | Iyas K | 3 | Done | Trainer
Sprint 25 | Team3 | T25-002 | Used Snyk to scan and identify vulnerabilities in project dependencies. | Muhammed Sinan | 3 | Done | Ogeti Aravind
Sprint 25 | Team3 | T25-003 | Used Snyk to scan and identify vulnerabilities in project dependencies. | Norah Elizabeth Biju | 3 | Done | Trainer
Sprint 25 | Team3 | T25-004 | Used Snyk to scan and identify vulnerabilities in project dependencies. | Bhogyam venkata sai Likhitha | 3 | Done | Muhammed Sinan
Sprint 25 | Team3 | T25-005 | Used Snyk to scan and identify vulnerabilities in project dependencies. | Ogeti Aravind | 3 | Done | Trainer
Sprint 25 | Team3 | T25-006 | Used Snyk to scan and identify vulnerabilities in project dependencies. | Mahesh D | 3 | Done | Norah Elizabeth Biju
Sprint 26 | Team3 | T26-001 | Set up SonarQube server and integrated it into CI pipeline for automated code analysis,snyk Integrated with the CI Pipeline | Iyas K | 5 | Done | Trainer
Sprint 26 | Team3 | T26-002 | Set up SonarQube server and integrated it into CI pipeline for automated code analysis,snyk Integrated with the CI Pipeline | Muhammed Sinan | 5 | Done | Mahesh D
Sprint 26 | Team3 | T26-003 | Set up SonarQube server and integrated it into CI pipeline for automated code analysis,snyk Integrated with the CI Pipeline | Norah Elizabeth Biju | 5 | Done | Trainer
Sprint 26 | Team3 | T26-004 | Set up SonarQube server and integrated it into CI pipeline for automated code analysis,snyk Integrated with the CI Pipeline | Bhogyam venkata sai Likhitha | 5 | Done | Iyas K
Sprint 26 | Team3 | T26-005 | Set up SonarQube server and integrated it into CI pipeline for automated code analysis,snyk Integrated with the CI Pipeline | Ogeti Aravind | 5 | Done | Trainer
Sprint 26 | Team3 | T26-006 | Set up SonarQube server and integrated it into CI pipeline for automated code analysis,snyk Integrated with the CI Pipeline | Mahesh D | 5 | Done | Bhogyam venkata sai Likhitha
Sprint 27 | Team3 | T27-001 | Implemented CI pipeline to build Docker images, perform Trivy image scanning, and push to DockerHub. | Iyas K | 8 | Done | Trainer
Sprint 27 | Team3 | T27-002 | Implemented CI pipeline to build Docker images, perform Trivy image scanning, and push to DockerHub. | Muhammed Sinan | 8 | Done | Norah Elizabeth Biju
Sprint 27 | Team3 | T27-003 | Implemented CI pipeline to build Docker images, perform Trivy image scanning, and push to DockerHub. | Norah Elizabeth Biju | 8 | Done | Trainer
Sprint 27 | Team3 | T27-004 | Implemented CI pipeline to build Docker images, perform Trivy image scanning, and push to DockerHub. | Bhogyam venkata sai Likhitha | 8 | Done | Mahesh D
Sprint 27 | Team3 | T27-005 | Implemented CI pipeline to build Docker images, perform Trivy image scanning, and push to DockerHub. | Ogeti Aravind | 8 | Done | Trainer
Sprint 27 | Team3 | T27-006 | Implemented CI pipeline to build Docker images, perform Trivy image scanning, and push to DockerHub. | Mahesh D | 8 | Done | Iyas K

## Sprint-Overview(Sample)
Sprint | Sprint Goal | Start Date | End Date | Deliverable
Sprint 1 | VM & Docker Setup | 2026-02-23 | 2026-02-21 | App running in Docker
Sprint 2 | CI/CD Implementation | 2026-02-24 | 2026-02-28 | Working Jenkins pipeline
Sprint 3 | Terraform & Infra | 2026-03-03 | 2026-03-07 | Infra provisioned via Terraform
Sprint 4 | Kubernetes Deployment | 2026-03-10 | 2026-03-14 | App deployed in K8s

## Task_Tracking(Sample)
Sprint | Team | Task ID | Task Description | Assigned To | Story Points | Status | Reviewer
Sprint 1 | Team 1 | T1-001 | Install Ubuntu on EC2 and configure SSH | Arun Simon | 3 | Done | Trainer
Sprint 1 | Team 1 | T1-002 | Setup Git and push sample project to GitHub | Sathvik NB Math | 2 | In Progress | Arun Simon
Sprint 1 | Team 1 | T1-003 | Install Docker and run nginx container | Preethi TK | 3 | Code Review | Trainer
Sprint 1 | Team 2 | T2-001 | Launch EC2 and configure security groups | Gokul | 3 | Done | Trainer
Sprint 1 | Team 2 | T2-002 | Build Docker image for sample Java app | Aswin | 5 | In Progress | Gokul
Sprint 1 | Team 2 | T2-003 | Push Docker image to DockerHub | Johaan | 2 | To Do | -
Sprint 1 | Team 3 | T3-001 | Setup Jenkins on EC2 | Neeraj | 5 | Blocked | Trainer
Sprint 1 | Team 3 | T3-002 | Create basic CI pipeline (Build Stage) | Jayadev | 5 | In Progress | Neeraj
Sprint 1 | Team 4 | T4-001 | Write Terraform script to create EC2 | Chriss Philip Saji | 8 | To Do | Trainer
Sprint 1 | Team 4 | T4-002 | Configure remote backend for Terraform | Abhinav | 5 | Backlog | -